## Seite 1
The "window idea" applied in project controlling
PROJECT GMBH |  | Project report | [8 empty] | Project manager:
Project designation: NORGE-AUSTRIA
Comparision of planned/budgeted and actual figures | [6 empty] | Forecast to the project end
Project structure (Sub- projects, project packages) | Planned |  | Budgeted |  | Actual |  | Still necessary |  | Actual figures expected |  |  | Variance announced
| Hours | Costs/CM | Hours | Costs/ CM | Hours | Costs/ CM | Hours | Costs/ CM | Hours | Costs/ CM | Date | Costs/ CM | Date
Total/date
Individual costs of the project
Absolute contribution margin
Contribution margin in %
Analysis of the project process (in brief outlines) | [6 empty] | Measures (state only few main points) |  |  |  |  | Who? | Date
Subjects to be discussed
1
% of com-
pletion
Papers of the Controller Akademie

## Seite 2
COMPANY: |  | PROJECT REPORT:COSTS & INVESTMENT |  |  |  | DISTRIBUTE TO:
|  | PROJECT: |  |  |  | PROJECT MANAGER:
| Project duration: |  | Reporting date 22.10.19..
Project-no. | Project phase (work packages, orders) | Initial budget | Budget last valid | Comple- ted*) | Dis-- posed**) | Total cost expected at project end | Variance expected at project end
Total
| *) completed = invoiced incl. on-account payments |  |  | **) Disposed = completed plus purchase orders (commitments)
ANALYSES:
(Unusual occurrences as e.g. important deliveries, high commitments, current situation as to target dates with enclosure, if necessary, reasons for act. and exp. variances concerning costs, performances and dates, important structural and organizational project changes etc.)
MEASURES: | [5 empty] | RESPONSIBLE | DATE
Continuation on the subsequent pages
2
19..
1
3
4
The project reports are available to the project managers for information and use on hard disk,A , directory PROJBER . After the document has been processed /established by the project manager, the reports are transmitted to the controlling service at the time intervals agreed. In a meeting, the controlling service discusses together with the project managers possible adaptations, modifications and additions and is responsible for passing the reports on to the departments / persons concerned.
2
Papers of the Controller Akademie
19..
1
3
4
2
20..
1
3
4
2
20..
1
3
4
2

## Seite 3
Project report for director of Research & Development
PROJECT REPORT |  | Date: |  | Reason for the report:
Project name: |  |  |  | Monthly report
Project number: |  |  |  | Milestone
Reporter: |  |  |  | Special reason
Brief description:
Project assessment |  |  | Planned, actual and expected figures:
Before | Target elements | now | Month
| Quality/performance/function |  | Costs
| Date |  | in ........
Costs
Space for further target elements
Milestones
Explanations and further actions
Responsible persons: |  |  | Dates: |  | Date:
Project manager: |  |  | Project start
Sub-Projects |  |  | Planned end of project
Expected end of project
Signatures: |  |  | Project approval
Project manager: |  |  | Last project meeting
Ordered by: |  |  | Next project meeting